## Slide 1
GRAPHIC 6 • EXECUTION PLAN
A 12- to 24-month plan with value in every phase
Visibility and one policy point first, federation last, and a slice of a real use case live at every milestone.
PHASE 01 • MONTHS 1–3
Inventory & gateway
Scan and register every agent, API and MCP server
Route LLM and MCP traffic through AI Gateway
Baseline token spend and data flows
Stand up a governance council and autonomy tiers
Value: Spend and risk visible by use case, unused agents retired, first use-case slice live
Exit: 80%+ of known agents registered, new LLM traffic via the gateway
PHASE 02 • MONTHS 4–8
Unlock & route
Expose the top 10–20 capabilities as APIs and MCP tools
Enable intelligent model routing and token limits
Publish context-engineering standards
Report cost per resolved task
Value: New agents reuse governed capabilities, and routine work moves to lower-cost models
Exit: Top capabilities reusable by any agent, cost per outcome reported
PHASE 03 • MONTHS 9–14
Autonomy & trust
Trusted Agent Identity with bounded delegation
Enforce tiers and bind approvals to actions
Evaluation in every release pipeline
Drill the kill switch and approvers, and red-team monthly
Value: Agents act in systems of record under bound approvals. Use-case KPI targets met
Exit: Every production agent has an identity, tier and eval baseline
PHASE 04 • MONTHS 15–24
Federated control plane
Multi-agent orchestration via Agent Broker and A2A
Post-quantum migration for control-plane traffic
Federate discovery and registries across domains
Swap models without app changes
Value: All goals met. Use cases at full run rate, and new ones start on shared controls
Exit: Federated discovery live, PQC plan on track for 2030
Sources: endnotes 1, 20, 21, 29, 79, 81.
26
Notes: Value comes first: this is a reference architecture adopted incrementally, and every phase delivers something the business can see. The research supports the approach: 56% of CEOs report no significant financial benefit from AI so far, yet strong AI foundations make meaningful returns three times more likely [79]. High performers build a repeatable capability instead of accumulating pilots [80], and successful deployments start in adjacent processes, prove clear value, then scale into core workflows, with top performers moving from pilot to full implementation in about 90 days [81]. Each phase is funded against the value the previous one proved.
By Phase 4 the organization has an agile, model-agnostic control plane that can swap models without recoding applications, and each use case runs at its full run rate.
Why this sequence:
Phase 1 is visibility plus a single policy point: Agent Scanners and Agent Registry for inventory, AI Gateway for LLM and MCP traffic, and a governance council and published autonomy tiers (the first 90 days of the CDO Magazine plan [29]). Start new policies in audit mode, then enforce, as Microsoft's Cloud Adoption Framework recommends [14]. Value: spend and risk visible by use case, unused agents retired, and the first use-case slice live in assist mode.
Phase 2 opens up the enterprise: expose the highest-value capabilities through MuleSoft APIs and MCP Bridge, then turn on model routing and token-based rate limits so cost per outcome becomes measurable [21]. Value: every new agent reuses governed capabilities, and routine work moves to lower-cost models.
Phase 3 hardens trust: Trusted Agent Identity with bounded delegation, enforced tiers with approvals bound to the actions they authorize, kill-switch and approver drills, evaluation in release pipelines and monthly red-teaming. Value: agents can act in systems of record under bound approvals, which is where most of each use case's business case sits.
Phase 4 federates: multi-agent orchestration across domains through Agent Broker and A2A, post-quantum migration for control-plane traffic ahead of the 2030–2031 federal deadlines, and discovery and registries federated across domains. Value: all goals met, with new use cases starting on shared controls.
Bain [20] supports doing federated discovery and cross-domain routing last, because they add complexity that is only justified once governance and orchestration are mature.
Credit: John Fisher, The AI Control Plane: Executive Briefing (2026), slide 26, licensed under CC BY-NC-ND 4.0: https://creativecommons.org/licenses/by-nc-nd/4.0/. The full deck, with its speaker notes and notices: https://johnfisher-ai.github.io/ai-control-plane-handbook/deck/. You may adapt this slide, with credit, under the additional permission in the deck’s notices: https://johnfisher-ai.github.io/ai-control-plane-handbook/deck/notices.html#permission.
Bracketed numbers in these notes, and endnote numbers on the slide, refer to the endnotes in Appendix B of The AI Control Plane Handbook: https://johnfisher-ai.github.io/ai-control-plane-handbook/handbook/appendix-b.html.